## Spreadsheet
Project | Project Description | Project Dependency (Dependent On) | POC | Description of Dependency | Schedule Impacts | Dependency Direction (Critical (red) Moderate (yellow) Nominal (green) | Dependency Direction Scale

## Example
Project | Project Description | Project Dependency (Dependent On) | POC | Description of Dependency | Schedule Impacts | Dependency Direction (Critical (red) Moderate (yellow) Nominal (green) | Dependency Direction Scale
HDR II (Rich Beaudoin) | HDR II replaces HDR IMS and stores discrete data rather than messages. Enables providers to obtain integrated data views and acquire the patient-specific clinical information needed to support treatment decisions. HDR II will serve as the primary source of clinical data for the legal record. | HDR DW | Clark Timmons | Performs daily extracts from HDR | Development for migrating DW from IMS to HDRII stopped - this will delay the shut down of IMS. |  | Critical - No primary/core functionality without the stated dependency
|  | HDR Hx | Clark Timmons | A Historical repository for clinical data that is accessed for all Order Check Allergy data requests | Currently in production - not impacted by the pause in development |  | Moderate - Some limited impact upon functionality, but primary/core functions would still be preserved
|  | CHDR | Dick Rickard | Provides the service to perform read and write functions with the DoD | Development for migrating CHDR from IMS to HDRII stopped - this will delay the shut down of IMS |  | Nominal - No known, but possible risk/impact
|  | Common Services | Carlos Hernandez | Provides critical technical components including NDS/CAIP, message transformation, | Currently supporting production - not impacted by pause
|  | EELS | Ricky Stephens | Provides Enterprise Exception Handling services | Development and testing with HDR placed on hold
|  | Home Telehealth | Dan Mahoney | Sends messages to the HDR from the Home Telehealth participants | Currently in production - not impacted by pause
|  | MPI | Danila Manapsal | Provides for patient correlation functions and registers the HDR as a system of interest once a patient's data is stored in the HDR | Currently in production - not impacted by pause
|  | My Health Vet | Randy Brown | Performs allergy queries to the HDR to support the veterans | MHV continuing development - on HDR v 2.1.1, deferment requested. No Impact
|  | PRE | Grant Tucker | Will read and write clinical data to the HDR | HDR support with the development of an integrated test site continues
|  | PSIM | Robin Rivera | Will replace MPI patient correlation functions | NO impact identified
|  | RDI | Dick Rickard | Performs Order Check data queries for every order written in VHA | Release of the next RDI version continues as an HDR/CDS v 2.1.0 production support activity
|  | VHIM | David Alvey | Provides templates and services for the VHIM messaging protocols | Development activity with the VHIM paused
|  | VIE | Mike Domanski | Processes all HL7 writes messages from the 128 Vista Systems and the communication with CHDR | Development and testing activities continue with HDRII/CDS v 2.1.1
|  | VistaWeb | Ed Ridley | Read Client to support VA clinicians | Development and testing activities continue with HDRII/CDS v 2.1.1
|  | CDCO | Pam Gutierrez | Provides 24x7 support for all production, testing and development hardware platforms. Provides for data storage. | Production support continues. Installation of new hardware continues. Release support for v 2.1.1 continue
Clinical Data Service (Rich Beaudoin) | CDS is the gateway to the Health Data Repository. CDS is the data abstraction layer than applications utilize to retrieve and send data to the HDR. | HDR DW | Clark Timmons | Performs daily extracts from HDR | Development for migrating DW from IMS to HDRII stopped - this will delay the shut down of IMS
|  | HDR Hx | Clark Timmons | A Historical repository for clinical data that is accessed for all Order Check Allergy data requests | Currently in production - not impacted by the pause in development
|  | CHDR | Dick Rickard | Provides the service to perform read and write functions with the DoD | Development for migrating CHDR from IMS to HDRII stopped - this will delay the shut down of IMS
|  | Common Services | Carlos Hernandez | Provides critical technical components including NDS/CAIP, message transformation, | Currently supporting production - not impacted by pause
|  | EELS | Ricky Stephens | Provides Enterprise Exception Handling services | Development and testing with HDR placed on hold
|  | Home Telehealth | Dan Mahoney | Sends messages to the HDR from the Home Telehealth participants | Currently in production - not impacted by pause
|  | MPI | Danila Manapsal | Provides for patient correlation functions and registers the HDR as a system of interest once a patient's data is stored in the HDR | Currently in production - not impacted by pause
|  | My Health Vet | Randy Brown | Performs allergy queries to the HDR to support the veterans | MHV continuing development - on HDR v 2.1.1, deferment requested. No Impact
|  | PRE | Grant Tucker | Will read and write clinical data to the HDR | HDR support with the development of an integrated test site continues
|  | PSIM | Robin Rivera | Will replace MPI patient correlation functions | No impact identified
|  | RDI | Dick Rickard | Performs Order Check data queries for every order written in VHA | Release of the next RDI version continues as an HDR/CDS v 2.1.0 production support activity
|  | VHIM | David Alvey | Provides templates and services for the VHIM messaging protocols | Development activity with the VHIM paused.
|  | VIE | Mike Domanski | Processes all HL7 writes messages from the 128 Vista Systems and the communication with CHDR | Development and testing activities continue with HDRII/CDS v 2.1.1
|  | VistaWeb | Ed Ridley | Read Client to support VA clinicians | Development and testing activities continue with HDRII/CDS v 2.1.1
|  | CDCO | Pam Gutierrez | Provides 24x7 support for all production, testing and development hardware platforms. Provides for data storage. | Production support continues. Installation of new hardware continues. Release support for v 2.1.1 continue.
HDR Data Warehouse (Clark Timmins) | HDR DW stores all clinical data in the HDR for the purpose of sharing with all non-patient care giving applications. | HDR Hx | Clark Timmons |  | DW 1+ (current production, current development, and future development) dependent on HDR Hx for data feed
|  | HDR IMS | Rich Beaudoin |  | DW 1.0 (current production) dependent on HDR IMS for data feed
|  | HDR II v2.1.0 | Rich Beaudoin |  | DW 2+ (current development) dependent on HDR II v2.1.0 for data feed
|  | Oracle 11g / Tech Refresh | Rob Thurmond Eric Robertson |  | DW 2.2+ (as-planned future development) dependent on Oracle 11g features
Administrative Data Repository (Mike Dore) | ADR provides an authoritative data store for shared administrative/demographic/eligibility information which is managed as a corporate asset. His will be realized by a central administrative database for all HeV applications. | SDS | Glen Crandall | The Standard Data Service (SDS) project consists of architecture service components to support the migration from VistA to the new HealtheVet framework. The major purpose of SDS is to provide a centralized repository of standard (non-clinical) administrative data and person data, a data maintenance mechanism plus a distribution capability to transport valid data to ADR and back to VistA. | Without timely reciept of SDS Updates ADR cannot release on time.
|  | CDCO | Roy McBrayer | Provides Operational database support through Service Level Agreements | Timely AITC support to ADR for maintenance, database releases, and updates is vital to the ability to deliver on time and 24/7 accessability for ADR clients.
|  | ESR | Brian Morgan | Healthevet Common service having overall project responsibility for the design and fielding of the Enrollment application. The authoritative source that provides eligibility and enrollment requirements to the ADR. | Without timely reciept of detailed requirements ADR cannot deliver on time.
|  | PSIM | Robin Rivera | HealtheVet Common Service source which is the authoritative service for VHA identity management. Provides identity data requirements to the ADR. | Without timely reciept of detailed requirements ADR cannot deliver on time
|  | RSA | Ed Syms | Has the responsibility for the creation, completion and revisiion of scheduling replacement. Provides scheduling data requirements to the ADR. | Without timely reciept of detailed requirements ADR cannot deliver on time.